## BIM (MoM)
Mircron Attendees List | CTCI Attendees List | QP Attendees List | Status | Raised Date | Item Number | Item Description | Action Required |  | Who | Due Date | Conclusion
| Willie, Tao |  | closed | 2026-04-24 | 0424-1 | BIM | We would like to request a demonstration from C2D on how to generate the models required by the Singapore Authorities (SGP Authority). Specifically, we need guidance on how to input the required parameters, which specific parameters are mandatory, and how the parameter mapping process should be executed. | oK |  |  | Information
[7 empty] | After the session, could C2D provide the guide book material to CTCI? | OK
|  |  | closed | 2026-04-24 | 0424-2 | BIM | Regarding the final submission to the SGP Authority, should we submit a single federated (integrated) IFC model, or should each discipline generate its own individual IFC file? If a federated model is required, which party is responsible for its production? | Only F10E2依照建築範圍，各自分開.IFC CSA要分棟去切 |  |  | Information
|  |  | closed | 2026-04-24 | 0424-3 | BIM | What are the procedures and criteria for clash detection in Singapore? Furthermore, what are the specific clash standards or tolerances required by the authorities? | rolling update |  |  | Information
|  |  |  | 2026-04-24 | 0424-4 | BIM | We understand that for each GateWay review, there is an opportunity to replace files via an Addendum, provided it does not affect the GFA (Gross Floor Area). Does this definition of "area" include the boundaries or areas of fire compartments? | 要問IDA， MEP僅 sanitary
|  |  |  | 2026-04-24 | 0424-5 | BIM | Regarding the MEP scope, since FF (Fire Fighting), HVAC, and PB (Plumbing) are the primary focus of the review, does this mean other systems do not need to be submitted for authority approval? | 僅design gateway Construction gateway要再檢討
|  |  |  | 2026-04-24 | 0424-6
[6 empty] | Other | For IC layout, we still tracking IDA to give us more detail design information, we will give you the first hand information when we have it